## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | BSDT (Blind Spot Detection & Tracker)
PROJECT MANAGER | Badrul Amin Bin Ismail Nasaruddin (B031910475)
GROUP NAME | Muhammad Luqman Bin Mohd Azman (B031910487) Syed Muhammad Harith Bin Syed Abdul Rahaman (B031910496)
COMPANY NAME | Blackbox sdn.bhd
DATE | 2021-08-10 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (days) | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Luqman | 2021-10-04 | 17/04/2021 | 7 | 100%
1.2 | Task Division | Badrul | 14/04/2021 | 17/04/2021 | 3 | 100%
1.3 | Project Charter Revisions | Badrul | 14/04/2021 | 17/04/2021 | 3 | 100%
1.4 | Research about accident statistic in Malaysia | Harith | 14/04/2021 | 2021-05-05 | 21 | 100%
1.5 | Deciding which problem that need help the most | Harith | 2021-02-05 | 2021-09-05 | 7 | 100%
1.6 | Research on what cause the problem | Harith | 2021-06-05 | 13/05/2021 | 7 | 100%
1.7 | Stakeholders | Badrul | 2021-10-05 | 20/05/2021 | 10 | 50%
1.8 | Meeting with client | Badrul | 17/05/2021 | 18/05/2021 | 1 | 50%
1.9 | Project Definition & Planning
2 | Scope & Goal Setting | Luqman | 15/05/2021 | 18/05/2021 | 3 | 100%
2.1 | Research on problem solving | Harith | 15/05/2021 | 29/05/2021 | 14 | 100%
2.2 | Deciding which algorithm is the best in term of accuracy and performance for obejct detection | Luqman | 26/05/2021 | 2021-09-06 | 14 | 50%
2.3 | Research on hardware | Badrul | 2021-06-06 | 20/06/2021 | 14 | 50%
2.4 | Budget Planning | Badrul | 17/06/2021 | 2021-01-07 | 14 | 50%
2.5 | Calculating the price for the whole hardware | Badrul | 28/06/2021 | 2021-05-07 | 7 | 70%
2.6 | Circuit Design on Simulation | Luqman | 2021-02-07 | 16/07/2021 | 14 | 50%
2.7 | Circuit Testing on Simulation | Luqman | 13/07/2021 | 27/07/2021 | 14 | 50%
2.8 | Design the object detection algorithm | Luqman | 24/07/2021 | 2021-07-08 | 14 | 50%
2.9 | Communication Plan | Harith | 2021-04-08 | 2021-11-08 | 7 | 50%
3 | Deciding which communication instrument is suitable | Harith | 2021-08-08 | 15/08/2021 | 7 | 70%
3.1 | Project Launch & Execution
3.2 | Project Task Tracking | Badrul | 2021-12-08 | 19/08/2021 | 7 | 50%
3.3 | Coding | Luqman | 16/08/2021 | 2021-06-09 | 21 | 40%
3.4 | Debugging | Luqman | 2021-03-09 | 17/09/2021 | 14 | 0%
3.5 | Object Detection Test | Luqman | 14/09/2021 | 21/09/2021 | 7 | 0%
3.6 | Build the circuit | Badrul | 18/09/2021 | 2021-02-10 | 14 | 50%
3.7 | Testing connection on the circuit | Badrul | 29/09/2021 | 13/10/2021 | 14 | 50%
3.8 | Testing hardware functionality | Badrul | 2021-10-10 | 17/10/2021 | 7 | 50%
3.9 | Project Testing | Harith | 14/10/2021 | 28/10/2021 | 14 | 0%
4 | Monitoring | Harith | 25/10/2021 | 2021-08-11 | 14 | 40%
4.1 | Project Performance / Monitoring
4.2 | Project Objectives | Harith | 2021-05-11 | 2021-12-11 | 7 | 0%
4.3 | Quality Deliverables | Harith | 2021-09-11 | 16/11/2021 | 7 | 0%
4.4 | Effort & Cost Tracking | Badrul | 13/11/2021 | 20/11/2021 | 7 | 40%
4.5 | Project Performance | Luqman | 17/11/2021 | 2021-01-12 | 14 | 20%
4.6 | Project Demostration | Luqman | 28/11/2021 | 29/11/2021 | 1 | 0%