## Sheet1
PROJECT TITLE | BSDT
PROJECT MANAGER | Badrul Amin (b031910475)
GROUP NAME | Muhammad Luqman (b031910487) Syed Muhammad Harith (b031910496)
COMPANY NAME | BlackBox Sdn. Bhd.
| #Units/Hrs/Mnth. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Project Management |  |  |  | 93600 | 95.89%
Project manager | 25 | 1440 | 36000
Project team members 1 | 20 | 1440 | 28800
Project team members 2 | 20 | 1440 | 28800
2. Hardware |  |  |  | 1240 | 1.27%
Lidar sensor | 130 | 4 | 520
Camera module | 35 | 1 | 35
Arduino uno | 120 | 1 | 120
Resistor | 7 | 3 | 21
Led | 6 | 2 | 12
Connector | 6 | 10 | 60
Switch | 10 | 1 | 10
Casing | 70 | 1 | 70
Battery | 40 | 2 | 80
Battery Connector | 9 | 2 | 18
Logistic Cost | 2 | 150 | 300
3. Software |  |  |  | 240 | 0.246%
Google Colab Pro | 6 | 40 | 240
4. Testing(10% of total hardware and software cost |  |  | 148 | 148 | 0.15%
5. Others |  |  |  | 1932 | 1.979%
Postpaid for nternet | 42 | 6 | 252
Travel cost for Project Manager | 12 | 70 | 840
Travel cost for Project team members 1 | 12 | 70 | 840
Travel cost for Project team members 2 | 12 | 70 | 840
Total project cost estimate |  |  |  | 97610