## Instructions
Instructions
1) Add or Delete project roles as applicable to your project
2) Insert key tasks and deliverables by phase
3) For each task select the appropriate assignment based on the resources involvement in that particular task. (A legend is provided in cell A3)

## Group
PROJECT TITLE | BSDT
PROJECT MANAGER | Badrul Amin (b031910475)
GROUP NAME | Muhammad Luqman (b031910487) Syed Muhammad Harith (b031910496)
COMPANY NAME | BlackBox Sdn. Bhd.

## Consolidated RAM
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Manager | Programmer | Circuit Engineer | Financial Analyst | Articial Intelligent Engineer | Data Engineer | Technical Manager | Implementation Manager | Test Manager | Finance Project Manager | Operations Manager | Project Sponsor | Legal Counsel
Project Funding
Task/Deliverable | P | I | I | P | I | I | I | S | I | P | P | A | I
Project Planning
Task/Deliverable | P | S | S | S | S | S | S | S | S | S | S | I | S
Contracting
Task/Deliverable | bar: P to I
Requirements Analysis
Task/Deliverable | P | S | S | I | S | I | S | S | I | I | S | I | A
Object Classification Design
Task/Deliverable | A | S | I | I | P | A | S | S | S | I | P | I | I
Dataset Engineering
Task/Deliverable | A | S | I | I | A | P | I | S | I | I | P | I | I
Circuit Design
Task/Deliverable | A | S | P | I | S | I | S | S | S | I | P | I | I
Programming
Task/Deliverable | A | P | S | I | A | S | S | S | S | I | P | I | I
System Testing
Task/Deliverable | A | S | S | I | S | S | P | P | P | I | P | I | I
System Implementation
Task/Deliverable | A | S | S | I | S | S | P | P | P | I | P | I | I
Resources
P
A
S
I